## Findings Summary
DemoCloud, Inc. – AWS Security Audit: Findings Summary
CIS AWS Foundations Benchmark v1.5.0 – Level 1 ¦ Audit Period: Jan 20 – Feb 5, 2026 ¦ Auditor: Mihir Trivedi
Finding ID | Title | CIS Control ID | Risk Rating | Affected Resource | Status | Remediation Owner | Due Date | Closed Date | Notes
F-001 | Public S3 Bucket – demoapp-bucket | 2.1.2 | Critical | s3://demoapp-bucket (us-east-1) | CLOSED | Priya Sharma (DevOps Lead) | 2026-02-10 | 2026-02-10 | Block Public Access enabled; ACL set private; credentials rotated
F-002 | Root Account Missing MFA | 1.5 | High | AWS Root Account (482177369043) | CLOSED | Daniel Okafor (Infra Eng) | 2026-02-11 | 2026-02-11 | Virtual MFA (Google Authenticator) enrolled on root
F-003 | Overly Permissive IAM Policy (s3:*) | 1.16 | High | IAM User: AdminUser / OverlyPermissiveS3Policy | CLOSED | Priya Sharma (DevOps Lead) | 2026-02-12 | 2026-02-12 | Inline policy deleted; scoped managed policy DemoApp-S3-LeastPrivilege attached
F-004 | CloudTrail Disabled in us-west-2 & eu-west-1 | 3.1 | Medium | CloudTrail: demoapp-trail (single-region) | CLOSED | Daniel Okafor (Infra Eng) | 2026-02-12 | 2026-02-12 | Trail updated to multi-region; IsMultiRegionTrail=true confirmed
F-005 | Security Group Allows SSH from 0.0.0.0/0 | 5.2 | Low | sg-0a3f9c7b2d1e4f8a0 (demoapp-sg-web, us-east-1) | CLOSED | Priya Sharma (DevOps Lead) | 2026-02-13 | 2026-02-13 | SSH restricted to 203.0.113.45/32 (Corp VPN); 0.0.0.0/0 rule revoked
AUDIT SUMMARY SCORECARD
Total Findings | 5
Critical | 1
High | 2
Medium | 1
Low | 1
Compliant Items | 4
All Remediated? | YES

## Re-audit Validation
Re-audit Validation – All Findings Verified Closed (February 14, 2026)
Finding ID | Title | Initial Rating | Initial Status | Re-audit Date | Post-Remediation Status | Validator Notes
F-001 | Public S3 Bucket – demoapp-bucket | Critical | OPEN | 2026-02-10 | CLOSED | Block Public Access: all 4 flags TRUE; ACL=private confirmed via CLI
F-002 | Root Account Missing MFA | High | OPEN | 2026-02-11 | CLOSED | AccountMFAEnabled=1 confirmed; virtual MFA active on root
F-003 | Overly Permissive IAM Policy (s3:*) | High | OPEN | 2026-02-12 | CLOSED | OverlyPermissiveS3Policy deleted; scoped policy verified via get-user-policy
F-004 | CloudTrail Multi-Region Gap | Medium | OPEN | 2026-02-12 | CLOSED | IsMultiRegionTrail=true; trail logging in us-east-1, us-west-2, eu-west-1
F-005 | SSH 0.0.0.0/0 in Security Group | Low | OPEN | 2026-02-13 | CLOSED | Only 203.0.113.45/32 ingress on port 22; confirmed via describe-security-groups

## Compliant Controls
Compliant CIS Controls – DemoCloud AWS Audit (Feb 2026)
CIS Control ID | Control Description | Category | Status | Observation
1.1 | Avoid use of root account for daily tasks | IAM | PASS | Credential report shows no root sign-in activity in past 90 days
1.14 | Hardware MFA for root (advisory) | IAM | PASS | Virtual MFA confirmed active; root daily-use is avoided per policy
2.1.1 | S3 versioning enabled on logging bucket | S3 | PASS | demoapp-logs-bucket: VersioningEnabled=true; lifecycle policy configured
3.3 | CloudTrail log file validation enabled | Logging | PASS | demoapp-trail: LogFileValidationEnabled=true confirmed via describe-trails

## Risk Dashboard
Risk Dashboard – DemoCloud AWS Security Audit (Feb 2026)
Risk Rating | Count | Status | Count
Critical | 1 | Open (Initial) | 5
High | 2 | Closed (Post-Remediation) | 5
Medium | 1
Low | 1
Overall Risk Level: | CRITICAL
Total Findings: | 5
Remediated: | 5 of 5 (100%)
Compliant Controls: | 4
Re-audit Date: | February 14, 2026